## Dashboard
ROADMAP 500K BERSIH / HARI — PAK HUSNUL
90-Day Revenue Operating System ¦ Hero Product: ModulAjar + BuatSoal ¦ Organic-first + Affiliate
INPUT & ASUMSI — EDIT JIKA BERUBAH |  | HERO PRODUCT & ASUMSI MIX
Target bersih / hari | 500000 | Produk | Harga | Mix | Weighted
Hari / bulan | 30 | ModulAjar Online | 149000 | 40%
Langganan AI / produk / bulan | 350000 | BuatSoal Online Pro | 149000 | 40%
Jumlah hero product | 2 | BuatSoal Online Max | 249000 | 20%
Domain / produk / tahun | 250000 | TOTAL / AOV |  | 100%
Komisi affiliate | 40%
Asumsi porsi gross dari affiliate | 25%
Weighted AOV |  | TARGET PER FASE
|  | Fase | Hari | Net / Hari | Net 30 Hari | Gross / Minggu
TARGET EKONOMI |  | Fase 1 | Hari 1–30 | 350000
Target bersih / bulan |  | Fase 2 | Hari 31–60 | 425000
Fixed cost / bulan |  | Fase 3 | Hari 61–90 | 500000
Retained factor setelah affiliate
Target gross / bulan |  | ATURAN STRATEGIS
Target gross / minggu |  | 1 | 80% marketing effort → ModulAjar + BuatSoal; produk lain = bonus/cross-sell/campaign khusus.
Kebutuhan transaksi / bulan |  | 2 | Jangan tambah kalender YouTube di workbook ini. Semua YouTube mengikuti file “YouTube Growth Plan — Pak Husnul — 90 Hari”.
Kebutuhan transaksi / hari |  | 3 | Post & Cuan tetap source of truth harian. Workbook ini hanya roll-up mingguan + keputusan revenue.
Kebutuhan transaksi / minggu |  | 4 | Promo diskon hanya event tertentu. Default campaign = harga normal + value/bonus/proof.
|  | 5 | Target utama = rolling 30 hari / mingguan; bukan memaksa Rp500K masuk tepat setiap hari.

## START HERE
PAK HUSNUL — MASTER CONTENT OPERATING SYSTEM ¦ 90 HARI
Tujuan | Mengintegrasikan Roadmap 500K/hari + YouTube Growth + daily content ModulAjar/BuatSoal + Sumber Belajar + Apps + WhatsApp menjadi satu kalender.
Prinsip | Jangan menambah pekerjaan. 1 Weekly Theme → Revenue + YouTube + Social + WA + Sumber Belajar + App.
Source of truth | Revenue: Roadmap 500K ¦ YouTube: YouTube Growth Plan ¦ Daily product content: TikTok + Threads ¦ Membership: Sumber Belajar
Prioritas | P0 Revenue daily + committed YouTube → P1 WA nurturing + repurpose → P2 signature membership → P3 eksperimen
Daily product rule | Minimal 1 konten/hari untuk ModulAjar Online atau BuatSoal Online. Kalender ini mengatur tema/arah, bukan menggantikan workflow posting Anda.
WhatsApp | Guru Mahir AI = public/warm pool. Aidukasi = closed/warmer pool.
Sumber Belajar | Mayoritas derived content dari YouTube, product content, apps, dan live. Jangan membuat kalender produksi terpisah.
Workbook tabs
MASTER CALENDAR | Satu baris per hari; kalender utama.
WEEKLY CLUSTERS | 13 tema mingguan yang menyatukan revenue + YouTube + membership.
SUMBER BELAJAR | Backlog/production schedule untuk 6 menu dan tier.
DAILY PRODUCT | Tracker harian ModulAjar/BuatSoal di TikTok + Threads.
YT ALIGNMENT | Jadwal YouTube dari workbook asli, tanpa menambah upload.
WA DISTRIBUTION | Ritme Guru Mahir AI + Aidukasi.
KPI DASHBOARD | KPI lintas mesin.
SOURCE REVENUE | Salinan 90-day revenue roadmap.
SOURCE YOUTUBE | Salinan 90-day YouTube roadmap.

## CONFIG
CONFIG & OPERATING RULES
Control Date | 2026-10-04
Revenue Hero Product | ModulAjar Online + BuatSoal Online
Daily Social Minimum | >= 1 post/day
Social Channels | TikTok + Threads
YouTube Cadence | Tue Long-form ¦ Wed Short ¦ Fri Long-form ¦ Sat Short ¦ Sun Live
WA Public Pool | Guru Mahir AI
WA Closed Pool | Aidukasi
Sumber Belajar Automated | Cron: Bank Prompt + AI Skills, 3x/day
Sumber Belajar Manual | Signature/deep-dive 1 per week max
Default Content Repurpose | YouTube/Product/App/Live → Prompt/Skill/Tutorial/Template/WA
Do Not Do | Jangan membuat kalender YouTube tambahan; jangan membuat Sumber Belajar sebagai pekerjaan terpisah.
Start Date | 2026-10-05
Plan End Date | 2027-01-02

## WEEKLY CLUSTERS
Week | Mulai | Selesai | Revenue Focus | Primary Campaign | YouTube Focus | YT Long-form #1 | YT Long-form #2 | YT Live | Membership Cluster | Sumber Belajar Outputs | Primary CTA | WA Focus | Revenue Target
1 | 2026-10-05 | 2026-10-11 | Reset & tracking | Post & Cuan reset + segmentasi | Reset positioning + bangun cluster Gemini/Deploy | Gemini Canvas ke Netlify: Cara Deploy Website Sampai Online | Saya Bikin Aplikasi Tanpa Bisa Coding — Ini Workflow Saya | Bikin Web App dari Nol dengan AI + Deploy | Reset & Tracking | Content library audit + tagging ¦ — | Contextual CTA | Tidak jualan keras 18 Agu; rapikan segment & next campaign. | 2450000
2 | 2026-10-12 | 2026-10-18 | Cross-sell #1 | ModulAjar → BuatSoal | Custom GPT cluster | Cara Membuat Custom GPT dari Nol — Sampai Bisa Dipakai | 7 Kesalahan Saat Membuat Custom GPT | Bikin Custom GPT untuk Membuat Soal | Cross-sell ModulAjar → BuatSoal | Cross-sell prompt/checklist ¦ Premium workflow | ModulAjar Online | WA sequence 4–5 sentuhan: edukasi → demo → proof → offer. | 2450000
3 | 2026-10-19 | 2026-10-25 | Acquisition sprint | Lead magnet masuk WA | PRD → aplikasi | Dari Ide → PRD → Aplikasi dengan AI | Tools AI Pembuat PRD: Saya Tes untuk Project Nyata | Dari Ide Kosong Jadi PRD + Prototype | Lead Magnet Acquisition | High-intent lead magnet ¦ — | Contextual CTA | TikTok/Threads → lead magnet → Guru Mahir AI. | 2450000
4 | 2026-10-26 | 2026-11-01 | Upgrade campaign | BuatSoal Pro → Max | Guru Bikin Aplikasi dimulai | Saya Bikin Aplikasi Absensi Siswa Pakai AI | Google Sheets Jadi Aplikasi dalam 30 Menit | Bikin Aplikasi Absensi Siswa dari Nol | BuatSoal Pro → Max | Assessment workflow resource ¦ Premium assessment workflow | BuatSoal Online | FAQ + demo pembeda Pro vs Max + CTA upgrade. | 2450000
5 | 2026-11-02 | 2026-11-08 | Lead Magnet Engine | 2 jalur lead magnet | Scale cluster pemenang + nilai siswa | Saya Bikin Aplikasi Nilai Siswa Pakai AI | Cara Update Website Netlify Tanpa Ganti Link | Bikin Aplikasi Nilai + Rekap Otomatis | Lead Magnet Engine | 2 lead-magnet tracks ¦ — | Contextual CTA | Target +150–200 lead baru/bulan mulai fase ini. | 2975000
6 | 2026-11-09 | 2026-11-15 | Affiliate Sprint #1 | Hero Week: ModulAjar | Gemini Gems + workflow guru | Cara Membuat Gemini Gems yang Benar | Saya Bikin AI Pembuat Soal dengan Gemini Gems | Bikin Asisten Soal Guru dengan Gemini | Hero Week: ModulAjar | Teacher planning resource cluster ¦ VIP teacher workflow | ModulAjar Online | WA grup affiliate: 1 briefing utama + 1 follow-up hasil. | 2975000
7 | 2026-11-16 | 2026-11-22 | Normal-price campaign | BuatSoal Online | Deploy + domain | Cara Pasang Custom Domain di Netlify untuk Pemula | Netlify vs Vercel: Mana Paling Mudah untuk Pemula? | Web AI → Deploy → Custom Domain LIVE | Hero Week: BuatSoal | Assessment resource cluster ¦ VIP assessment architect | BuatSoal Online | Lead magnet BuatSoal + case study + offer. | 2975000
8 | 2026-11-23 | 2026-11-29 | Normal-price campaign | ModulAjar Online | AI productivity + education crossover | Dari RPP Jadi PowerPoint dengan AI | 7 Prompt AI yang Menghemat Pekerjaan Guru | Bikin Media Pembelajaran dari RPP | AI untuk Perencanaan Pembelajaran | RPP → PPT Prompt + AI Skill + Cheatsheet ¦ Premium RPP→Presentation | ModulAjar Online | Nurture lead baru + proof existing customer. | 2975000
9 | 2026-11-30 | 2026-12-06 | Scale winner | Scale channel/campaign terbaik | Serial Guru Bikin Aplikasi | Bikin Aplikasi Kas Kelas dengan AI | Bikin Aplikasi Jurnal Mengajar dengan AI | Bikin Kas Kelas + Dashboard | Guru Bikin Aplikasi | Kas Kelas/Jurnal + App Builder resources ¦ Premium Teacher App Builder | Contextual CTA | Kurangi aktivitas yang tidak menghasilkan lead/sales. | 3500000
10 | 2026-12-07 | 2026-12-13 | Affiliate Sprint #2 | Hero Week: BuatSoal | Build in public produk nyata | Saya Bikin PosterEdu: Dari Masalah Jadi Aplikasi | Kenapa Aplikasi AI Saya Lambat? Ini Kesalahannya | Audit + Perbaiki Aplikasi AI yang Lambat | Build in Public Produk Nyata | PosterEdu/App performance workflow ¦ VIP implementation blueprint | BuatSoal Online | WA affiliate fokus objection handling + proof. | 3500000
11 | 2026-12-14 | 2026-12-20 | Cross-sell #2 | BuatSoal → ModulAjar | Marketplace / produk digital | Dari Aplikasi Jadi Produk Digital: Workflow Saya | Saya Tambahkan Marketplace ke Aplikasi Guru | Build Marketplace Sederhana dengan AI | Aplikasi → Produk Digital | Productization/marketplace templates ¦ Premium product system | ModulAjar Online | Segmented WA/DM; hindari broadcast ke semua orang. | 3500000
12 | 2026-12-21 | 2026-12-27 | Backend validation | Membership 9K + produk pendamping | Perbandingan tools berintent tinggi | ChatGPT vs Gemini untuk Bikin Aplikasi: Saya Tes | Lovable vs Google Apps Script + AI: Pilih Mana? | Battle Build: 2 Tools, 1 Aplikasi | AI Tools Comparison | Decision framework + tool workflow ¦ VIP build framework | Contextual CTA | Target 25–50 member aktif, tapi jangan korbankan hero-product sales. | 3500000
13 | 2026-12-28 | 2027-01-03 | 90-day scale decision | 500K/day run-rate | 90-day recap + next season | 90 Hari Membangun Channel AI: Apa yang Berhasil? | Saya Bikin Aplikasi Wali Kelas Tanpa Jadi Programmer | Final Build: Aplikasi Wali Kelas | 90-Day Recap & Next Season | Best-of library + Wali Kelas app cluster ¦ VIP next-season workshop | Contextual CTA | Pilih 1–2 engine untuk scale berikutnya; hentikan aktivitas low-ROI. | 3500000

## MASTER CALENDAR
Date | Day | Week | Weekly Theme | Revenue Focus | Daily Product Content | YouTube | Sumber Belajar / Repurpose | Apps | WA / Distribution | Primary CTA | Priority | Status | Notes
2026-10-05 | Monday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-06 | Tuesday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: Gemini Canvas ke Netlify: Cara Deploy Website Sampai Online | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-07 | Wednesday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: 1 public/free resource cleanup | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-08 | Thursday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: — | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-09 | Friday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Saya Bikin Aplikasi Tanpa Bisa Coding — Ini Workflow Saya | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-10 | Saturday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-11 | Sunday | 1 | Reset & Tracking | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Bikin Web App dari Nol dengan AI + Deploy | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-12 | Monday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-13 | Tuesday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | Long-form #1: Cara Membuat Custom GPT dari Nol — Sampai Bisa Dipakai | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-14 | Wednesday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: Cross-sell checklist | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-15 | Thursday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | — | AI Skill / Premium: Premium workflow | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-16 | Friday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | Long-form #2: 7 Kesalahan Saat Membuat Custom GPT | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-17 | Saturday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-18 | Sunday | 2 | Cross-sell ModulAjar → BuatSoal | ModulAjar → BuatSoal | ModulAjar → BuatSoal — min. 1 konten TikTok/Threads | LIVE: Bikin Custom GPT untuk Membuat Soal | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-19 | Monday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-20 | Tuesday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: Dari Ide → PRD → Aplikasi dengan AI | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-21 | Wednesday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: Lead magnet + landing resource | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-22 | Thursday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: — | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-23 | Friday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Tools AI Pembuat PRD: Saya Tes untuk Project Nyata | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-24 | Saturday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-25 | Sunday | 3 | Lead Magnet Acquisition | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Dari Ide Kosong Jadi PRD + Prototype | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-26 | Monday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-27 | Tuesday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | Long-form #1: Saya Bikin Aplikasi Absensi Siswa Pakai AI | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-28 | Wednesday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: Assessment prompt | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-29 | Thursday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | — | AI Skill / Premium: Premium assessment workflow | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-10-30 | Friday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | Long-form #2: Google Sheets Jadi Aplikasi dalam 30 Menit | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-10-31 | Saturday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-01 | Sunday | 4 | BuatSoal Pro → Max | BuatSoal Pro → Max | BuatSoal Pro → Max — min. 1 konten TikTok/Threads | LIVE: Bikin Aplikasi Absensi Siswa dari Nol | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-02 | Monday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-03 | Tuesday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: Saya Bikin Aplikasi Nilai Siswa Pakai AI | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-04 | Wednesday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: 2 lead magnet resources | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-05 | Thursday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: — | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-06 | Friday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Cara Update Website Netlify Tanpa Ganti Link | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-07 | Saturday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-08 | Sunday | 5 | Lead Magnet Engine | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Bikin Aplikasi Nilai + Rekap Otomatis | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-09 | Monday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-10 | Tuesday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | Long-form #1: Cara Membuat Gemini Gems yang Benar | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-11 | Wednesday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: ModulAjar workflow | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-12 | Thursday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | — | AI Skill / Premium: VIP teacher workflow | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-13 | Friday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | Long-form #2: Saya Bikin AI Pembuat Soal dengan Gemini Gems | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-14 | Saturday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-15 | Sunday | 6 | Hero Week: ModulAjar | Hero Week: ModulAjar | Hero Week: ModulAjar — min. 1 konten TikTok/Threads | LIVE: Bikin Asisten Soal Guru dengan Gemini | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Past | Committed YouTube slot from source plan.
2026-11-16 | Monday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | BuatSoal Online | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-17 | Tuesday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | Long-form #1: Cara Pasang Custom Domain di Netlify untuk Pemula | — | — | Share YT / proof / discussion | BuatSoal Online | P0 | Past | Committed YouTube slot from source plan.
2026-11-18 | Wednesday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: BuatSoal workflow | — | Free resource / lead magnet | BuatSoal Online | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-19 | Thursday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | — | AI Skill / Premium: VIP assessment architect | — | Deep education + contextual offer | BuatSoal Online | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-20 | Friday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | Long-form #2: Netlify vs Vercel: Mana Paling Mudah untuk Pemula? | — | — | Share YT + case/proof | BuatSoal Online | P0 | Past | Committed YouTube slot from source plan.
2026-11-21 | Saturday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | BuatSoal Online | P0 | Past | Do not add new long-form/live. Repurpose existing source asset.
2026-11-22 | Sunday | 7 | Hero Week: BuatSoal | BuatSoal Online | BuatSoal Online — min. 1 konten TikTok/Threads | LIVE: Web AI → Deploy → Custom Domain LIVE | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | BuatSoal Online | P0 | Today | Committed YouTube slot from source plan.
2026-11-23 | Monday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | ModulAjar Online | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-11-24 | Tuesday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | Long-form #1: Dari RPP Jadi PowerPoint dengan AI | — | — | Share YT / proof / discussion | ModulAjar Online | P0 | Planned | Committed YouTube slot from source plan.
2026-11-25 | Wednesday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: RPP→PPT prompt + AI Skill | — | Free resource / lead magnet | ModulAjar Online | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-11-26 | Thursday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | — | AI Skill / Premium: Premium RPP→Presentation | — | Deep education + contextual offer | ModulAjar Online | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-11-27 | Friday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | Long-form #2: 7 Prompt AI yang Menghemat Pekerjaan Guru | — | — | Share YT + case/proof | ModulAjar Online | P0 | Planned | Committed YouTube slot from source plan.
2026-11-28 | Saturday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | ModulAjar Online | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-11-29 | Sunday | 8 | AI untuk Perencanaan Pembelajaran | ModulAjar Online | ModulAjar Online — min. 1 konten TikTok/Threads | LIVE: Bikin Media Pembelajaran dari RPP | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | ModulAjar Online | P0 | Planned | Committed YouTube slot from source plan.
2026-11-30 | Monday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | Kas Kelas / Jurnal Mengajar — app content cluster | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-01 | Tuesday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: Bikin Aplikasi Kas Kelas dengan AI | — | Kas Kelas / Jurnal Mengajar — app content cluster | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-02 | Wednesday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: App + prompt + tutorial | Kas Kelas / Jurnal Mengajar — app content cluster | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-03 | Thursday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: Premium Teacher App Builder | Kas Kelas / Jurnal Mengajar — app content cluster | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-04 | Friday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Bikin Aplikasi Jurnal Mengajar dengan AI | — | Kas Kelas / Jurnal Mengajar — app content cluster | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-05 | Saturday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | Kas Kelas / Jurnal Mengajar — app content cluster | Resource + reminder | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-06 | Sunday | 9 | Guru Bikin Aplikasi | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Bikin Kas Kelas + Dashboard | Capture ideas from LIVE → backlog minggu berikutnya | Kas Kelas / Jurnal Mengajar — app content cluster | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-07 | Monday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | — | — | PosterEdu / app performance — build in public | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-08 | Tuesday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | Long-form #1: Saya Bikin PosterEdu: Dari Masalah Jadi Aplikasi | — | PosterEdu / app performance — build in public | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-09 | Wednesday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: App workflow + troubleshooting | PosterEdu / app performance — build in public | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-10 | Thursday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | — | AI Skill / Premium: VIP implementation blueprint | PosterEdu / app performance — build in public | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-11 | Friday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | Long-form #2: Kenapa Aplikasi AI Saya Lambat? Ini Kesalahannya | — | PosterEdu / app performance — build in public | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-12 | Saturday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | PosterEdu / app performance — build in public | Resource + reminder | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-13 | Sunday | 10 | Build in Public Produk Nyata | Hero Week: BuatSoal | Hero Week: BuatSoal — min. 1 konten TikTok/Threads | LIVE: Audit + Perbaiki Aplikasi AI yang Lambat | Capture ideas from LIVE → backlog minggu berikutnya | PosterEdu / app performance — build in public | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-14 | Monday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-15 | Tuesday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | Long-form #1: Dari Aplikasi Jadi Produk Digital: Workflow Saya | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-16 | Wednesday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | Short #1 (repurpose long-form) | FREE / derived resource: PRD + marketplace template | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-17 | Thursday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | — | AI Skill / Premium: Premium product system | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-18 | Friday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | Long-form #2: Saya Tambahkan Marketplace ke Aplikasi Guru | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-19 | Saturday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-20 | Sunday | 11 | Aplikasi → Produk Digital | BuatSoal → ModulAjar | BuatSoal → ModulAjar — min. 1 konten TikTok/Threads | LIVE: Build Marketplace Sederhana dengan AI | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-21 | Monday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | — | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-22 | Tuesday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: ChatGPT vs Gemini untuk Bikin Aplikasi: Saya Tes | — | — | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-23 | Wednesday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: Tool decision cheatsheet | — | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-24 | Thursday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: VIP build framework | — | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-25 | Friday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Lovable vs Google Apps Script + AI: Pilih Mana? | — | — | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-26 | Saturday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | — | Resource + reminder | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-27 | Sunday | 12 | AI Tools Comparison | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Battle Build: 2 Tools, 1 Aplikasi | Capture ideas from LIVE → backlog minggu berikutnya | — | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-28 | Monday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | — | Aplikasi Wali Kelas — final build | Edukasi / problem awareness | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-29 | Tuesday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #1: 90 Hari Membangun Channel AI: Apa yang Berhasil? | — | Aplikasi Wali Kelas — final build | Share YT / proof / discussion | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2026-12-30 | Wednesday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #1 (repurpose long-form) | FREE / derived resource: Best-of + Wali Kelas app | Aplikasi Wali Kelas — final build | Free resource / lead magnet | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2026-12-31 | Thursday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | — | AI Skill / Premium: VIP next-season workshop | Aplikasi Wali Kelas — final build | Deep education + contextual offer | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2027-01-01 | Friday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Long-form #2: Saya Bikin Aplikasi Wali Kelas Tanpa Jadi Programmer | — | Aplikasi Wali Kelas — final build | Share YT + case/proof | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.
2027-01-02 | Saturday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | Short #2 (repurpose long-form) | Template / Others / App asset dari weekly cluster | Aplikasi Wali Kelas — final build | Resource + reminder | pakhusnul.id / contextual product | P0 | Planned | Do not add new long-form/live. Repurpose existing source asset.
2027-01-03 | Sunday | 13 | 90-Day Recap & Next Season | 500K/day run-rate | ModulAjar Online / BuatSoal Online — min. 1 konten (pilih sesuai angle) | LIVE: Final Build: Aplikasi Wali Kelas | Capture ideas from LIVE → backlog minggu berikutnya | Aplikasi Wali Kelas — final build | Live reminder + follow-up | pakhusnul.id / contextual product | P0 | Planned | Committed YouTube slot from source plan.

## SUMBER BELAJAR
ID | Week | Target Date | Source Asset | Menu | Content Title / Working Idea | Tier | Source Type | Production Effort | CTA | Status | Notes
SB-W01-01 | 1 | 2026-10-07 | Derived from YT/Product | Bank Prompt | 1 public/free resource cleanup | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W01-02 | 1 | 2026-10-08 | Derived / curated | AI Skills | AI Skill — Reset & Tracking | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W01-03 | 1 | 2026-10-10 | YouTube/Product/App | Others | Template / Cheatsheet — Reset & Tracking | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W02-01 | 2 | 2026-10-14 | Derived from YT/Product | Bank Prompt | Cross-sell checklist | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W02-02 | 2 | 2026-10-15 | Derived / curated | AI Skills | AI Skill — Cross-sell ModulAjar → BuatSoal | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W02-03 | 2 | 2026-10-17 | YouTube/Product/App | Others | Template / Cheatsheet — Cross-sell ModulAjar → BuatSoal | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W03-01 | 3 | 2026-10-21 | Derived from YT/Product | Bank Prompt | Lead magnet + landing resource | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W03-02 | 3 | 2026-10-22 | Derived / curated | AI Skills | AI Skill — Lead Magnet Acquisition | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W03-03 | 3 | 2026-10-24 | YouTube/Product/App | Others | Template / Cheatsheet — Lead Magnet Acquisition | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W04-01 | 4 | 2026-10-28 | Derived from YT/Product | Bank Prompt | Assessment prompt | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W04-02 | 4 | 2026-10-29 | Derived / curated | AI Skills | AI Skill — BuatSoal Pro → Max | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W04-03 | 4 | 2026-10-31 | YouTube/Product/App | Others | Template / Cheatsheet — BuatSoal Pro → Max | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W05-01 | 5 | 2026-11-04 | Derived from YT/Product | Bank Prompt | 2 lead magnet resources | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W05-02 | 5 | 2026-11-05 | Derived / curated | AI Skills | AI Skill — Lead Magnet Engine | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W05-03 | 5 | 2026-11-07 | YouTube/Product/App | Others | Template / Cheatsheet — Lead Magnet Engine | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W06-01 | 6 | 2026-11-11 | Derived from YT/Product | Bank Prompt | ModulAjar workflow | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W06-02 | 6 | 2026-11-12 | Derived / curated | AI Skills | AI Skill — Hero Week: ModulAjar | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W06-03 | 6 | 2026-11-14 | YouTube/Product/App | Others | Template / Cheatsheet — Hero Week: ModulAjar | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W06-04 | 6 | 2026-11-15 | Admin / Signature | Tutorial | Signature Guide — Hero Week: ModulAjar | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W07-01 | 7 | 2026-11-18 | Derived from YT/Product | Bank Prompt | BuatSoal workflow | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W07-02 | 7 | 2026-11-19 | Derived / curated | AI Skills | AI Skill — Hero Week: BuatSoal | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W07-03 | 7 | 2026-11-21 | YouTube/Product/App | Others | Template / Cheatsheet — Hero Week: BuatSoal | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W07-04 | 7 | 2026-11-22 | Admin / Signature | Tutorial | Signature Guide — Hero Week: BuatSoal | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W08-01 | 8 | 2026-11-25 | Derived from YT/Product | Bank Prompt | RPP→PPT prompt + AI Skill | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W08-02 | 8 | 2026-11-26 | Derived / curated | AI Skills | AI Skill — AI untuk Perencanaan Pembelajaran | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W08-03 | 8 | 2026-11-28 | YouTube/Product/App | Others | Template / Cheatsheet — AI untuk Perencanaan Pembelajaran | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W09-01 | 9 | 2026-12-02 | Derived from YT/Product | Bank Prompt | App + prompt + tutorial | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W09-02 | 9 | 2026-12-03 | Derived / curated | AI Skills | AI Skill — Guru Bikin Aplikasi | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W09-03 | 9 | 2026-12-05 | YouTube/Product/App | Others | Template / Cheatsheet — Guru Bikin Aplikasi | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W09-04 | 9 | 2026-12-06 | Admin / Signature | Tutorial | Signature Guide — Guru Bikin Aplikasi | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W09-05 | 9 | 2026-12-06 | App / Build | Apps | App Resource — Guru Bikin Aplikasi | PUBLIC/FREE | App | Medium | Try App / Join Member | Planned | App dapat punya akses tier sendiri.
SB-W10-01 | 10 | 2026-12-09 | Derived from YT/Product | Bank Prompt | App workflow + troubleshooting | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W10-02 | 10 | 2026-12-10 | Derived / curated | AI Skills | AI Skill — Build in Public Produk Nyata | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W10-03 | 10 | 2026-12-12 | YouTube/Product/App | Others | Template / Cheatsheet — Build in Public Produk Nyata | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W10-04 | 10 | 2026-12-13 | Admin / Signature | Tutorial | Signature Guide — Build in Public Produk Nyata | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W10-05 | 10 | 2026-12-13 | App / Build | Apps | App Resource — Build in Public Produk Nyata | PUBLIC/FREE | App | Medium | Try App / Join Member | Planned | App dapat punya akses tier sendiri.
SB-W11-01 | 11 | 2026-12-16 | Derived from YT/Product | Bank Prompt | PRD + marketplace template | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W11-02 | 11 | 2026-12-17 | Derived / curated | AI Skills | AI Skill — Aplikasi → Produk Digital | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W11-03 | 11 | 2026-12-19 | YouTube/Product/App | Others | Template / Cheatsheet — Aplikasi → Produk Digital | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W11-04 | 11 | 2026-12-20 | Admin / Signature | Tutorial | Signature Guide — Aplikasi → Produk Digital | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W12-01 | 12 | 2026-12-23 | Derived from YT/Product | Bank Prompt | Tool decision cheatsheet | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W12-02 | 12 | 2026-12-24 | Derived / curated | AI Skills | AI Skill — AI Tools Comparison | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W12-03 | 12 | 2026-12-26 | YouTube/Product/App | Others | Template / Cheatsheet — AI Tools Comparison | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W12-04 | 12 | 2026-12-27 | Admin / Signature | Tutorial | Signature Guide — AI Tools Comparison | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W12-05 | 12 | 2026-12-27 | App / Build | Apps | App Resource — AI Tools Comparison | PUBLIC/FREE | App | Medium | Try App / Join Member | Planned | App dapat punya akses tier sendiri.
SB-W13-01 | 13 | 2026-12-30 | Derived from YT/Product | Bank Prompt | Best-of + Wali Kelas app | FREE | Repurpose | Low | Free Member / pakhusnul.id | Planned | Diturunkan dari weekly theme; tidak membuat topik terpisah.
SB-W13-02 | 13 | 2026-12-31 | Derived / curated | AI Skills | AI Skill — 90-Day Recap & Next Season | PREMIUM | Repurpose/Curated | Medium | Upgrade Premium | Planned | Cron dapat memasok volume; admin memilih skill yang paling relevan.
SB-W13-03 | 13 | 2027-01-02 | YouTube/Product/App | Others | Template / Cheatsheet — 90-Day Recap & Next Season | FREE | Repurpose | Low | Free Member | Planned | Gunakan output yang sudah dibuat; jangan menambah produksi besar.
SB-W13-04 | 13 | 2027-01-03 | Admin / Signature | Tutorial | Signature Guide — 90-Day Recap & Next Season | PREMIUM | Manual | High | Upgrade Premium | Planned | Satu signature asset maksimal per minggu; pilih hanya jika workload aman.
SB-W13-05 | 13 | 2027-01-03 | App / Build | Apps | App Resource — 90-Day Recap & Next Season | PUBLIC/FREE | App | Medium | Try App / Join Member | Planned | App dapat punya akses tier sendiri.

## DAILY PRODUCT
Date | Week | Campaign Focus | Recommended Product | TikTok/Threads Minimum | Content Angle | CTA | Status | Published? | Link / Notes
2026-10-05 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-10-06 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-10-07 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-10-08 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2026-10-09 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2026-10-10 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2026-10-11 | 1 | Post & Cuan reset + segmentasi | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned
2026-10-12 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Pain point | ModulAjar Online | Planned
2026-10-13 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Education | ModulAjar Online | Planned
2026-10-14 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Demo | ModulAjar Online | Planned
2026-10-15 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Use case | ModulAjar Online | Planned
2026-10-16 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Feature | ModulAjar Online | Planned
2026-10-17 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Proof/Testimonial | ModulAjar Online | Planned
2026-10-18 | 2 | ModulAjar → BuatSoal | ModulAjar Online | >= 1 post | Offer/CTA | ModulAjar Online | Planned
2026-10-19 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-10-20 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-10-21 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-10-22 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2026-10-23 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2026-10-24 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2026-10-25 | 3 | Lead magnet masuk WA | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned
2026-10-26 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Pain point | BuatSoal Online | Planned
2026-10-27 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Education | BuatSoal Online | Planned
2026-10-28 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Demo | BuatSoal Online | Planned
2026-10-29 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Use case | BuatSoal Online | Planned
2026-10-30 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Feature | BuatSoal Online | Planned
2026-10-31 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Proof/Testimonial | BuatSoal Online | Planned
2026-11-01 | 4 | BuatSoal Pro → Max | BuatSoal Online | >= 1 post | Offer/CTA | BuatSoal Online | Planned
2026-11-02 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-11-03 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-11-04 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-11-05 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2026-11-06 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2026-11-07 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2026-11-08 | 5 | 2 jalur lead magnet | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned
2026-11-09 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Pain point | ModulAjar Online | Planned
2026-11-10 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Education | ModulAjar Online | Planned
2026-11-11 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Demo | ModulAjar Online | Planned
2026-11-12 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Use case | ModulAjar Online | Planned
2026-11-13 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Feature | ModulAjar Online | Planned
2026-11-14 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Proof/Testimonial | ModulAjar Online | Planned
2026-11-15 | 6 | Hero Week: ModulAjar | ModulAjar Online | >= 1 post | Offer/CTA | ModulAjar Online | Planned
2026-11-16 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Pain point | BuatSoal Online | Planned
2026-11-17 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Education | BuatSoal Online | Planned
2026-11-18 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Demo | BuatSoal Online | Planned
2026-11-19 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Use case | BuatSoal Online | Planned
2026-11-20 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Feature | BuatSoal Online | Planned
2026-11-21 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Proof/Testimonial | BuatSoal Online | Planned
2026-11-22 | 7 | BuatSoal Online | BuatSoal Online | >= 1 post | Offer/CTA | BuatSoal Online | Planned
2026-11-23 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Pain point | ModulAjar Online | Planned
2026-11-24 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Education | ModulAjar Online | Planned
2026-11-25 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Demo | ModulAjar Online | Planned
2026-11-26 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Use case | ModulAjar Online | Planned
2026-11-27 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Feature | ModulAjar Online | Planned
2026-11-28 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Proof/Testimonial | ModulAjar Online | Planned
2026-11-29 | 8 | ModulAjar Online | ModulAjar Online | >= 1 post | Offer/CTA | ModulAjar Online | Planned
2026-11-30 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-12-01 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-12-02 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-12-03 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2026-12-04 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2026-12-05 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2026-12-06 | 9 | Scale channel/campaign terbaik | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned
2026-12-07 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Pain point | BuatSoal Online | Planned
2026-12-08 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Education | BuatSoal Online | Planned
2026-12-09 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Demo | BuatSoal Online | Planned
2026-12-10 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Use case | BuatSoal Online | Planned
2026-12-11 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Feature | BuatSoal Online | Planned
2026-12-12 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Proof/Testimonial | BuatSoal Online | Planned
2026-12-13 | 10 | Hero Week: BuatSoal | BuatSoal Online | >= 1 post | Offer/CTA | BuatSoal Online | Planned
2026-12-14 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Pain point | ModulAjar Online | Planned
2026-12-15 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Education | ModulAjar Online | Planned
2026-12-16 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Demo | ModulAjar Online | Planned
2026-12-17 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Use case | ModulAjar Online | Planned
2026-12-18 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Feature | ModulAjar Online | Planned
2026-12-19 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Proof/Testimonial | ModulAjar Online | Planned
2026-12-20 | 11 | BuatSoal → ModulAjar | ModulAjar Online | >= 1 post | Offer/CTA | ModulAjar Online | Planned
2026-12-21 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-12-22 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-12-23 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-12-24 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2026-12-25 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2026-12-26 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2026-12-27 | 12 | Membership 9K + produk pendamping | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned
2026-12-28 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Pain point | Pilih hero product sesuai angle | Planned
2026-12-29 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Education | Pilih hero product sesuai angle | Planned
2026-12-30 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Demo | Pilih hero product sesuai angle | Planned
2026-12-31 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Use case | Pilih hero product sesuai angle | Planned
2027-01-01 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Feature | Pilih hero product sesuai angle | Planned
2027-01-02 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Proof/Testimonial | Pilih hero product sesuai angle | Planned
2027-01-03 | 13 | 500K/day run-rate | ModulAjar Online / BuatSoal Online | >= 1 post | Offer/CTA | Pilih hero product sesuai angle | Planned

## YT ALIGNMENT
Week | Start | End | Focus | Long-form #1 | Long-form #2 | Live | Shorts | Watch Target | Review | Integration Rule
1 | 2026-10-05 | 2026-10-11 | Reset positioning + bangun cluster Gemini/Deploy | Gemini Canvas ke Netlify: Cara Deploy Website Sampai Online | Saya Bikin Aplikasi Tanpa Bisa Coding — Ini Workflow Saya | Bikin Web App dari Nol dengan AI + Deploy | 2 | 25 | Cek CTR + retention 30 detik | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
2 | 2026-10-12 | 2026-10-18 | Custom GPT cluster | Cara Membuat Custom GPT dari Nol — Sampai Bisa Dipakai | 7 Kesalahan Saat Membuat Custom GPT | Bikin Custom GPT untuk Membuat Soal | 2 | 30 | Bandingkan search vs browse | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
3 | 2026-10-19 | 2026-10-25 | PRD → aplikasi | Dari Ide → PRD → Aplikasi dengan AI | Tools AI Pembuat PRD: Saya Tes untuk Project Nyata | Dari Ide Kosong Jadi PRD + Prototype | 2 | 35 | Catat pertanyaan audience | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
4 | 2026-10-26 | 2026-11-01 | Guru Bikin Aplikasi dimulai | Saya Bikin Aplikasi Absensi Siswa Pakai AI | Google Sheets Jadi Aplikasi dalam 30 Menit | Bikin Aplikasi Absensi Siswa dari Nol | 2 | 40 | Pilih 2 cluster terbaik bulan 1 | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
5 | 2026-11-02 | 2026-11-08 | Scale cluster pemenang + nilai siswa | Saya Bikin Aplikasi Nilai Siswa Pakai AI | Cara Update Website Netlify Tanpa Ganti Link | Bikin Aplikasi Nilai + Rekap Otomatis | 2 | 50 | Update thumbnail video CTR rendah | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
6 | 2026-11-09 | 2026-11-15 | Gemini Gems + workflow guru | Cara Membuat Gemini Gems yang Benar | Saya Bikin AI Pembuat Soal dengan Gemini Gems | Bikin Asisten Soal Guru dengan Gemini | 2 | 60 | Perkuat end-screen chain | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
7 | 2026-11-16 | 2026-11-22 | Deploy + domain | Cara Pasang Custom Domain di Netlify untuk Pemula | Netlify vs Vercel: Mana Paling Mudah untuk Pemula? | Web AI → Deploy → Custom Domain LIVE | 2 | 70 | Cek suggested traffic antarvideo | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
8 | 2026-11-23 | 2026-11-29 | AI productivity + education crossover | Dari RPP Jadi PowerPoint dengan AI | 7 Prompt AI yang Menghemat Pekerjaan Guru | Bikin Media Pembelajaran dari RPP | 2 | 80 | Review 8 minggu: stop topik lemah | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
9 | 2026-11-30 | 2026-12-06 | Serial Guru Bikin Aplikasi | Bikin Aplikasi Kas Kelas dengan AI | Bikin Aplikasi Jurnal Mengajar dengan AI | Bikin Kas Kelas + Dashboard | 2 | 95 | Optimasi playlist series | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
10 | 2026-12-07 | 2026-12-13 | Build in public produk nyata | Saya Bikin PosterEdu: Dari Masalah Jadi Aplikasi | Kenapa Aplikasi AI Saya Lambat? Ini Kesalahannya | Audit + Perbaiki Aplikasi AI yang Lambat | 2 | 110 | Cari peak retention untuk format authority | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
11 | 2026-12-14 | 2026-12-20 | Marketplace / produk digital | Dari Aplikasi Jadi Produk Digital: Workflow Saya | Saya Tambahkan Marketplace ke Aplikasi Guru | Build Marketplace Sederhana dengan AI | 2 | 125 | Periksa subscriber gained/video | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
12 | 2026-12-21 | 2026-12-27 | Perbandingan tools berintent tinggi | ChatGPT vs Gemini untuk Bikin Aplikasi: Saya Tes | Lovable vs Google Apps Script + AI: Pilih Mana? | Battle Build: 2 Tools, 1 Aplikasi | 2 | 140 | Tentukan signature format final | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.
13 | 2026-12-28 | 2027-01-03 | 90-day recap + next season | 90 Hari Membangun Channel AI: Apa yang Berhasil? | Saya Bikin Aplikasi Wali Kelas Tanpa Jadi Programmer | Final Build: Aplikasi Wali Kelas | 2 | 160 | Audit 90 hari + plan Q4 berikutnya | LOCKED: no additional long-form/live from revenue or membership calendar. Repurpose only.

## WA DISTRIBUTION
Day | Guru Mahir AI (Public/Warm) | Aidukasi (Closed/Warmer) | Purpose | Typical CTA | Do Not
Monday | Problem awareness / education | Deeper problem framing | Start weekly theme | Soft: lihat resource | Jangan hard sell
Tuesday | Share YouTube + insight | Share YouTube + context | Authority/proof | Watch / discuss | Jangan bikin konten baru
Wednesday | Free prompt/resource | Free + deeper explanation | Lead/member activation | Free Member / resource | Jangan gate semua hal
Thursday | Practical tutorial | Deep workflow + offer | Education → conversion | Premium/product | Jangan spam
Friday | Share YouTube + case | Case study / proof | Authority + trust | Product contextual | Jangan broadcast semua segment
Saturday | Resource / checklist | Resource + reminder | Utility/retention | Free/Premium | Jangan over-post
Sunday | Live reminder + follow-up | Live + next-step resource | Engagement | Join Live / member area | Jangan jualan keras

## KPI DASHBOARD
KPI DASHBOARD — MASTER CONTENT OPERATING SYSTEM
Metric | Target / Rule | Actual | Status | Notes
Net Revenue / 30D | From revenue roadmap |  |  | North Star
Daily Product Content | >=1 post/day |  |  | TikTok + Threads
YT Long-form | 2/week |  |  | Tue + Fri
YT Live | 1/week |  |  | Sun
YT Shorts | 2/week |  |  | Wed + Sat
Sumber Belajar derived | 2–4/week |  |  | Do not overproduce
Signature asset | <=1/week |  |  | Only if workload safe
WA touchpoints | 5–7/week |  |  | Segmented by pool
Free → Premium | Track conversion |  |  | Membership
Premium → VIP | Track conversion |  |  | Membership
Apps shipped/shared | Track by week |  |  | Public/Free/Premium/VIP

## SOURCE REVENUE
90-DAY REVENUE ROADMAP
Tanggal diselaraskan dengan YouTube Growth Plan; revenue roadmap tidak menambah kewajiban upload YouTube.
Week | Mulai | Selesai | Fase | Fokus Revenue | Primary Campaign | Audience Utama | Key Revenue Action | Affiliate Action | WA / Lead Action | Koordinasi YouTube (NO OVERLAP) | Net Target / Minggu | Gross Target / Minggu | Status
1 | 2026-10-05 | 2026-10-11 | Fase 1 | Reset & tracking | Post & Cuan reset + segmentasi | Seluruh customer existing | Backfill uang Juli–Agustus seperlunya; segmentasi ModulAjar/BuatSoal; promo Merdeka selesai 17 Agu. | Audit affiliate aktif; jangan rekrut besar dulu. | Tidak jualan keras 18 Agu; rapikan segment & next campaign. | Ikuti YT Plan Week 1. Revenue hanya pasang CTA/lead magnet pada aset yang memang dibuat. | 2450000 |  | Planned
2 | 2026-10-12 | 2026-10-18 | Fase 1 | Cross-sell #1 | ModulAjar → BuatSoal | ModulAjar-only | Campaign edukasi: setelah modul selesai, lanjut ke asesmen. Offer BuatSoal normal price. | Affiliate fokus ModulAjar/BuatSoal; beri angle problem-solution. | WA sequence 4–5 sentuhan: edukasi → demo → proof → offer. | Gunakan output YT minggu ini sebagai proof/repurpose bila relevan; jangan buat video YouTube tambahan. | 2450000 |  | Planned
3 | 2026-10-19 | 2026-10-25 | Fase 1 | Acquisition sprint | Lead magnet masuk WA | Cold/warm audience baru | Aktifkan 1 lead magnet high-intent dan tracking sumber lead. | Minta affiliate kirim traffic ke hero product / lead asset yang disepakati. | TikTok/Threads → lead magnet → Guru Mahir AI. | YouTube tetap mengikuti plan. Potong/reuse aset YT untuk TikTok/Threads, bukan produksi topik baru. | 2450000 |  | Planned
4 | 2026-10-26 | 2026-11-01 | Fase 1 | Upgrade campaign | BuatSoal Pro → Max | ±100 user Pro | Offer upgrade bayar selisih jika arsitektur produk memungkinkan; target 15–20 upgrade. | Affiliate tidak jadi fokus utama untuk upgrade existing buyer. | FAQ + demo pembeda Pro vs Max + CTA upgrade. | Jangan jadwalkan live/video YT tambahan; gunakan demo yang sudah ada. | 2450000 |  | Planned
5 | 2026-11-02 | 2026-11-08 | Fase 2 | Lead Magnet Engine | 2 jalur lead magnet | Audience baru | Pisahkan lead magnet ModulAjar vs BuatSoal agar intent lebih jelas. | Berikan affiliate landing/angle khusus per hero product. | Target +150–200 lead baru/bulan mulai fase ini. | YT = discovery/authority. Revenue workbook hanya menentukan destination CTA. | 2975000 |  | Planned
6 | 2026-11-09 | 2026-11-15 | Fase 2 | Affiliate Sprint #1 | Hero Week: ModulAjar | Affiliate existing | Target affiliate aktif ≥5; ukur sales/active affiliate dan new-customer rate. | Brief mingguan ModulAjar + kit + leaderboard sederhana. | WA grup affiliate: 1 briefing utama + 1 follow-up hasil. | Tidak perlu konten YT khusus affiliate; gunakan materi dari YouTube plan sebagai sales asset. | 2975000 |  | Planned
7 | 2026-11-16 | 2026-11-22 | Fase 2 | Normal-price campaign | BuatSoal Online | Guru butuh asesmen/soal | Campaign normal price berbasis demo, use case, testimonial, bukan diskon. | Hero Week: BuatSoal. | Lead magnet BuatSoal + case study + offer. | YT Plan tetap punya kalendernya sendiri; revenue hanya bridge ke produk/lead magnet. | 2975000 |  | Planned
8 | 2026-11-23 | 2026-11-29 | Fase 2 | Normal-price campaign | ModulAjar Online | Guru butuh perencanaan | Campaign normal price ModulAjar; audit CTA dan conversion dari WA. | Hero Week: ModulAjar. | Nurture lead baru + proof existing customer. | Repurpose insight dari YT; tidak membuat long-form/live tambahan. | 2975000 |  | Planned
9 | 2026-11-30 | 2026-12-06 | Fase 3 | Scale winner | Scale channel/campaign terbaik | Segment dengan conversion tertinggi | Double down hanya pada channel + offer yang terbukti 8 minggu pertama. | Affiliate target aktif 10–15. | Kurangi aktivitas yang tidak menghasilkan lead/sales. | Gunakan cluster pemenang YT sebagai sumber konten lintas channel. | 3500000 |  | Planned
10 | 2026-12-07 | 2026-12-13 | Fase 3 | Affiliate Sprint #2 | Hero Week: BuatSoal | Affiliate + audience baru | Dorong affiliate new-customer acquisition; ukur gross vs net setelah komisi. | Target 10–15 affiliate aktif; coaching top performer. | WA affiliate fokus objection handling + proof. | Tidak menambah video YT. Materi YT hanya masuk marketing kit jika relevan. | 3500000 |  | Planned
11 | 2026-12-14 | 2026-12-20 | Fase 3 | Cross-sell #2 | BuatSoal → ModulAjar | BuatSoal-only | Reverse cross-sell ke customer yang belum punya ModulAjar. | Affiliate tetap hero-product campaign; cross-sell existing dilakukan direct. | Segmented WA/DM; hindari broadcast ke semua orang. | Gunakan konten YT sebagai authority; offer dilakukan di owned channel. | 3500000 |  | Planned
12 | 2026-12-21 | 2026-12-27 | Fase 3 | Backend validation | Membership 9K + produk pendamping | Buyer paling loyal | Validasi membership 9K sebagai retention layer; produk lain sebagai backend, bukan hero. | Ajak customer loyal yang cocok menjadi affiliate/advocate. | Target 25–50 member aktif, tapi jangan korbankan hero-product sales. | YouTube tetap fokus growth plan; membership hanya CTA opsional jika konteksnya cocok. | 3500000 |  | Planned
13 | 2026-12-28 | 2027-01-03 | Fase 3 | 90-day scale decision | 500K/day run-rate | Semua winning segment | Audit 90 hari: revenue mix, channel, customer baru, affiliate, campaign winner. Tetapkan Q4. | Target affiliate aktif 20+ bila kualitas pipeline mendukung. | Pilih 1–2 engine untuk scale berikutnya; hentikan aktivitas low-ROI. | Review bersama KPI YouTube, tetapi roadmap Q4 tetap memisahkan tujuan growth vs revenue. | 3500000 |  | Planned

## SOURCE YOUTUBE
Week | Mulai | Selesai | Fase | Fokus Mingguan | Long-form #1 | Long-form #2 | LIVE | Shorts | Target Watch Hours | Review Mingguan | Status
1 | 05/10/2026 | 11/10/2026 | Repositioning | Reset positioning + bangun cluster Gemini/Deploy | Gemini Canvas ke Netlify: Cara Deploy Website Sampai Online | Saya Bikin Aplikasi Tanpa Bisa Coding — Ini Workflow Saya | Bikin Web App dari Nol dengan AI + Deploy | 2 | 25 | Cek CTR + retention 30 detik | Planned
2 | 12/10/2026 | 18/10/2026 | Repositioning | Custom GPT cluster | Cara Membuat Custom GPT dari Nol — Sampai Bisa Dipakai | 7 Kesalahan Saat Membuat Custom GPT | Bikin Custom GPT untuk Membuat Soal | 2 | 30 | Bandingkan search vs browse | Planned
3 | 19/10/2026 | 25/10/2026 | Repositioning | PRD → aplikasi | Dari Ide → PRD → Aplikasi dengan AI | Tools AI Pembuat PRD: Saya Tes untuk Project Nyata | Dari Ide Kosong Jadi PRD + Prototype | 2 | 35 | Catat pertanyaan audience | Planned
4 | 26/10/2026 | 01/11/2026 | Repositioning | Guru Bikin Aplikasi dimulai | Saya Bikin Aplikasi Absensi Siswa Pakai AI | Google Sheets Jadi Aplikasi dalam 30 Menit | Bikin Aplikasi Absensi Siswa dari Nol | 2 | 40 | Pilih 2 cluster terbaik bulan 1 | Planned
5 | 02/11/2026 | 08/11/2026 | Double Down | Scale cluster pemenang + nilai siswa | Saya Bikin Aplikasi Nilai Siswa Pakai AI | Cara Update Website Netlify Tanpa Ganti Link | Bikin Aplikasi Nilai + Rekap Otomatis | 2 | 50 | Update thumbnail video CTR rendah | Planned
6 | 09/11/2026 | 15/11/2026 | Double Down | Gemini Gems + workflow guru | Cara Membuat Gemini Gems yang Benar | Saya Bikin AI Pembuat Soal dengan Gemini Gems | Bikin Asisten Soal Guru dengan Gemini | 2 | 60 | Perkuat end-screen chain | Planned
7 | 16/11/2026 | 22/11/2026 | Double Down | Deploy + domain | Cara Pasang Custom Domain di Netlify untuk Pemula | Netlify vs Vercel: Mana Paling Mudah untuk Pemula? | Web AI → Deploy → Custom Domain LIVE | 2 | 70 | Cek suggested traffic antarvideo | Planned
8 | 23/11/2026 | 29/11/2026 | Double Down | AI productivity + education crossover | Dari RPP Jadi PowerPoint dengan AI | 7 Prompt AI yang Menghemat Pekerjaan Guru | Bikin Media Pembelajaran dari RPP | 2 | 80 | Review 8 minggu: stop topik lemah | Planned
9 | 30/11/2026 | 06/12/2026 | Series Engine | Serial Guru Bikin Aplikasi | Bikin Aplikasi Kas Kelas dengan AI | Bikin Aplikasi Jurnal Mengajar dengan AI | Bikin Kas Kelas + Dashboard | 2 | 95 | Optimasi playlist series | Planned
10 | 07/12/2026 | 13/12/2026 | Series Engine | Build in public produk nyata | Saya Bikin PosterEdu: Dari Masalah Jadi Aplikasi | Kenapa Aplikasi AI Saya Lambat? Ini Kesalahannya | Audit + Perbaiki Aplikasi AI yang Lambat | 2 | 110 | Cari peak retention untuk format authority | Planned
11 | 14/12/2026 | 20/12/2026 | Series Engine | Marketplace / produk digital | Dari Aplikasi Jadi Produk Digital: Workflow Saya | Saya Tambahkan Marketplace ke Aplikasi Guru | Build Marketplace Sederhana dengan AI | 2 | 125 | Periksa subscriber gained/video | Planned
12 | 21/12/2026 | 27/12/2026 | Series Engine | Perbandingan tools berintent tinggi | ChatGPT vs Gemini untuk Bikin Aplikasi: Saya Tes | Lovable vs Google Apps Script + AI: Pilih Mana? | Battle Build: 2 Tools, 1 Aplikasi | 2 | 140 | Tentukan signature format final | Planned
13 | 28/12/2026 | 03/01/2027 | Series Engine | 90-day recap + next season | 90 Hari Membangun Channel AI: Apa yang Berhasil? | Saya Bikin Aplikasi Wali Kelas Tanpa Jadi Programmer | Final Build: Aplikasi Wali Kelas | 2 | 160 | Audit 90 hari + plan Q4 berikutnya | Planned